## Sheet1
Team: We Tried
November 12th 2021: Start our project, we began to analize requirements and find ideas for the website
Then I created a list of tasks and divided it up to each members of the group, and we started analyse and build the database.
Aplication part | Coder | Content | Status | Start date | Duration
Database | Nguyen Hoang Bich | Analyse, create tables and add data. | Done | 2021-11-12 | 1 day
Database | Nguyen Hoang Bich | Check database relation, fix and change some tables. | Done | 2021-11-14 | 15 days
Analyse website requirements | Nguyen Hoang Bich | List and divided tasks to other members | Done | 2021-11-14 | 15 day
Main website interface | Vu Thi Thom | Set main website interface. | Done | 2021-11-13 | 7 days
Admin manager module
Admin interface | Nguyen Hoang Bich | Design Admin interface. | Done | 2021-11-13 | 2 day
_Admin - Banner | Nguyen Hoang Bich | Show banners, add/update/delete functions. | Done | 2021-11-15 | 4 day
_Admin - Store | Nguyen Hoang Bich | Show store info ,update functions | Done | 2021-11-19 | 1 day
_Admin - User | Nguyen Hoang Bich | Show users, add/update/delete functions. | Done | 2021-11-20 | 1 day
_Admin - Product | Nguyen Hoang Bich | Show products, add/update/delete functions. | Done | 2021-11-21 | 1 day
_Admin - Category | Nguyen Hoang Bich | Show categories, add/update/delete functions. | Done | 2021-11-22 | 1 day
_Admin - Contact | Nguyen Hoang Bich | Show contact info, update functions | Done | 2021-11-23 | 1 day
_Admin - System | Nguyen Hoang Bich | Show contact info, update functions | Done | 2021-11-24 | 1 day
_Admin - Transaction and report | Nguyen Hoang Bich | Show cancelled and on going transactions, update functions - Show finished transactions and export function | Done | 2021-11-25 | 2 days
Admin interface | Nguyen Hoang Bich | Fix incompatible errors. | Done | 2021-11-13 | 5 days
User template
User interface | Vu Thi Thom | Design User interface | Done | 2021-11-13 | 3 days
_User - Profile | Vu Thi Thom | Show customer profile, update function. | Done | 2021-11-16 | 2 days
_User - Transaction list | Vu Thi Thom | Show customer's transaction list, search function. | Done | 2021-11-18 | 5 days
_User - Login/register | Vu Thi Thom | Set up login and sign up form. | Done | 2021-11-23 | 2 days
_User - Product list | Vu Thi Thom | Show product list, show modal product detail/ add to cart buttons. | Done | 2021-11-25 | 2 days
_User - Category list | Vu Thi Thom | Show categories list with search function. | Done | 2021-11-27 | 2 days
_User - Manage cart | Nguyen Hoang Bich | Show product in carts, change product's quantity/ remove product functions | Done | 2021-11-27 | 2 days
_User - Checkout | Nguyen Hoang Bich | Checkout with paypal function. | Done | 2021-11-29 | 2 days
_User - Search product | Vu Thi Thom | Filter products by name, price and categories. | Done | 2021-11-29 | 5 days
_User - Set up security | Nguyen Hoang Bich | Set up security (check account role to redirect) | Done | 2021-12-01 | 1 days
User interface | Nguyen Hoang Bich | Change database | Done | 2021-11-27 | 4 day
User interface | Nguyen Hoang Bich | Combine with admin interface. | Done | 2021-12-02 | 1 day
User interface | Nguyen Hoang Bich | Fix incompatible errors. | Done | 2021-12-04 | 3 day
User interface | Nguyen Hoang Bich | Check/fix bugs and validate data. | Done | 2021-11-27 | 11 days
Other
Validate data | Nguyen Hoang Bich | Validate and format data in all input fields. | Done | 2020-11-21 | 10 days
Test application | Vo Thi Thom | Test all functions. | Done | 2020-12-07 | 3 days
Rating | Nguyen Hoang Bich
Supporter | Vo Thi Thom
Tester | Vo Thi Thom
Reporter | Nguyen Hoang Bich